## 1 GIA
Gender impact assessments
Table 1 - Gender impact assessments progress
Required | Required | Required | Required | Required | Required | Recommended | Recommended
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Compliance and enforcement of embedded networks | Program | The commission provides effective regulatory oversight of existing embedded networks including consumer protection, licensing, compliance and enforcement. | For Review | No action taken | The GIA completed, allowed us to make fidings that identified a lack of data about gender and intersectionality for the consumers affected by this program. It did assist in identifying additional data collections and considerations that should be collected in future equivalent programs. | Yes | The commission has a strong focus on supporting vulnerable consumers, so intersectionality in that context was considered. There remains little data about the consumers living within embedded networks currently though to progress an impact assessment to this level.
Regulatory reforms in the Victorian Energy Upgrades program | Program | Implementation of new legislative reforms for the Victorian Energy Upgrades program, including new products, increased consumer protections, improved standards of compliance and new accreditation, compliance and enforcement tools for the commission | New | No action taken | The GIA identified a lack of data about gender and intersectionality for the consumers affected by this program. It did assist in identifying additional data that will be collected going forward about program participants. | Yes | The commission has a strong focus on supporting vulnerable consumers, so intersectionality in that context was considered, but with limited data at this stage. Future data requirements have been identified.
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review | Yes | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. | Yes | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Alison Roche (ESC) Reply: Hi @Alison Roche (ESC) , @Jessica Bryers (ESC) and I have our final writing session tomorrow. Do you need anything from us re this page? Also looking likely we may need you to type up the blurb for additional commentary that we discussed on Friday. Reply: All good, just haven't had a chance to get to it today (yet) but still hoping to. I'll think of some content for the blurb too and send it through in email (that bit will be tomorrow)

## 2.1 Strategies and measures
Strategies and measures
Table 2.1 - Strategies and measures progress
Required | Required | Required | Recommended | Recommended | Recommended | Recommended
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Indicators key
List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Relevant indicator(s) 1: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. | 1. 2. 3. 4. 5. 6. 7. | Gender composition of all levels of the workforce. Gender composition of governing bodies. Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender. Sexual harassment in the workplace Recruitment and promotion practices in the workplace. Availability and utilisation of terms, conditions and pratices relating to: - family violence leave - flexible working arrangements - working arrangements supporting employees with family or caring responsibilities Gendered segregation within the workplace
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | 1 | 2 | 3 | 4 | 5 | 6 | 7
Action 1.1 Encourage commission staff to share relevant intersectional data through a staff survey | Not started | While we have encouraged staff to participate in the People Matters survey to share their experiences and demographics with us, we have not progressed this action to what was committed by July 2022 as a specific internal DEI survey. We have committed to embedding DEI questions and data demographics collection into our survey program, including onboarding, pulse and grad surveys across 2024. |  | Due July 2022 | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 1
Action 1.2 Formation of diversity and inclusion action group | Complete | Our DEI Working Group was established in 2022, having a Commissioner (Board) sponsor and 20 members from across the commission, who provide feedback on DEI strategies, plan days of signifiance events and network and collaborate as a space of belonging. Committed to be completed by June 2022. Was completed by Janurary 2022. | The working group meets monthly, with a rotating chair and secretariat from across the group. The working group has successfully established an approach to planning events and writing comms, building awareness and understanding of DEI events such as International Women's Day and International Non-Binary People's Day. | Due June 2022 | People and Culture DEI Remit Sponsor | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 2
Action 2.1 Identify gender imbalances and identify strategies as required | Not started | This piece of work was not due to be completed until June 2025. We are addressing this as a part of broader gender pay gap and workforce composition project due to commence in 2024. |  | Due June 2025 | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 3
Action 3.1 Maintain balanced gender composition of our Governing Body by advocating to ensure this is considered in any recruitment for new commissioners | Ongoing | This piece of work is ongoing, as a commission our commissioners also serve as our governing body in the form of a board. Our governing body serves on 5 year terms, with requirements for executive search to maintain the Victorian governments board composition requirements of at least 50% of appointments and composition to be women. No difference to GEAP timelines agreed in 2021 as this is ongoing during the period of the GEAP. | We are currently undergoing executive search for a commissioner, and are following these requirements. | June 2021 - July 2025 | Chairperson | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 4
Action 4.1 Deeper dive into the data to see if trend is maintained in different roles | In progress | Not met by June 2023, but this action is now in progress due to a workforce composition analysis being undertaken as part of the 2023 progress reporting and audit. |  | Due July 2023 and Janurary 2025 | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 4
Action 5.1 Manager training on recruiting right including content on unconscious bias, wording PDs and adverts to appeal to all genders | In progress | Our manager recruitment toolkit is currently under review to include a section on inclusive hiring and recruitment, including gender neutral language and position descriptions. This is on track to be deployed across Q2 and Q3 of 2024. Managers will be supported on the launch of this toolkit, through information sessions and dedicated HR support to those undergoing significant hiring. We had this as a commitment to undertake annually across the GEAP period. | While the toolkit has not been refreshed, People and Culture have hired a dedicated DEI lead within the team to futher advance the great work done by our recruitment team in this space. They are well versed in flexibility, gender inclusivity and reducing bias in recruitment processes, and so have been advising on all new appointments and interview processes. This builds on the comitments already exisiting in our toolkit around gender balance on panels and a requirement for hiring managers to share our stance on flexibility and working arrangements as part of the interview process. | Annually in December | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 4
Action 5.2 Review PD and job advert templates to ensure wording appeals to all genders | Complete | In 2021 we updated our job advertisements and position description templates off the back of pandemic fueled gender inequality, to include a commitment to flexibility, diversity and caring responsibilties. This was completed in December 2022. We will continiously review in line with best practice over the period of our GEAP. | With a workforce composition of 131 women and 118 men in 2023, our commitments to gender inclusive recruitment, onboarding and hiring practices is having a positive effect in attracting those on flexible working arrangements (110 from People Matters Survey results with a 70% response rate) or those who have caring responsibilties (65 from People Matters Survey results with a 70% response rate). | Due December 2022 | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 4
Action 5.3 Creation and implementation of a diversity and inclusion plan which will include actions around recruitment and retention | Complete | Our Diversity, Equity, and Inclusion action plan was launched in 2023, with the planning, consultation and drafting process completed by December 2022. We engaged a provider in August 2022 to assist us with this process. This action plan has three key focus areas, one of which has several actions and commitments focused on driving a more inclusive recruitment processes, and actions focused on mentoring and career progression for marginlised groups aimed at retaining talent employees. | The development of this action plan involved interviews with the CEO, feedback during consultation of focus groups (16 staff) and assessing our current state and recent employee experience results against 14 leading practice DEI assessment criteria. The action plan recieved overwhelming endorsement and has been embedded through People and Culture processes and ways of working through workstreams. | Due September 2022 | People and Culture DEI Working Group | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 4
Action 5.4 Continue to ensure gender split on panels | Ongoing | As an ongoing practice, we are commited to providing advisory to hiring managers to ensure their panels have a gender spilt, and this requirement has been reflected in the recruitment process and toolkits. |  |  | People and Culture Hiring Managers | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Action 5.5 guidance for recruitment panels on ensuring fair interview and assessment process | In progress | Manager recruitment toolkit is currently under review, with new section on inclusive recruitment to be added, and to be launched in Q2 2024. Managers will be supported on this toolkit during this launch period. Did not meet June 2023 deadline, as we wanted to ensure this action aligned with the broader recruitment remit and the projects underway to improve processes. |  | Due June 2023 | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Action 5.6 Look further at skills and areas that certain genders may be drawn by seeking feedback from interns and graduates about their classes and gender balance | Not started | We did not meet our deadline of September 2023, as we paused this piece of work to be incoporated as part of a broader review looking at the employee experience of our graduates and interns, as well as redesigning our experience survey program of work offering. We have moved this to a December 2024 timeline to align with the summer intake of Interns. | N/A | Due September 2023 | People and Culture
Action 5.7 Intersectionality: Continue to participate in various VPS pathway programs e.g. Aboriginal and disability. | Ongoing | The commission regularly partakes in the Aboriginal pathway and disability pathway program adminsitered by the VPSC. This is an ongoing commitment across our GEAP period. | While we were not successful in gaining any graduates in the recent intake, we have had success across other intakes, and have a very large graduate and intern intake through other mediums. |  | People and Culture Hiring Managers | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Action 5.8 Ensure encouragement for diverse people to apply for roles is stated in all job adverts | Complete | In 2021 we updated our job advertisements and position description templates off the back of pandemic fueled gender inequality, to include a commitment to flexibility, diversity and caring responsibilties. This was completed in December 2022. We will continiously review in line with best practice over the period of our GEAP. | N/A | Due December 2022 | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Action 6.1 Support women in more male dominated university courses (e.g. economics) by providing mentors through the Department of Treasury and Finance mentoring women program or another program. If we cannot join a program create our own group or program | Not started | This action is a mix of ongoing and not yet started. Across the GEAP period, our Leadership and L&D remit is reviewing our mentoring and career progression opportunites. In 2023, we implemented a broader mentoring program offering in partnership with 3 VPS agencies, focused specifically on women. The timeline for this was September 2023, but has been delayed, due to needing to roll out the mentoring program to women first, to lay the foundations in our approach to gendered career progression. Further progress will be made in line with our gender pay gap and workforce composition reporting, to provide us with deeper insights to support how we then tailor the mentoring program and future career progression activities. We are also building a proposition to collaborate with Department of Treasury and Finance (Our parent department), to become invovled with their specialised program. | N/A | Due September 2023 | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Action 6.2 Send commission representatives to universities to promote opportunities for women and gender diverse people at the commission and why it is a great place to work | Void/cancelled | This action has been marked as void/cancelled due to the VPSC not sending EOIs in recent times to participate in promoting grad programs at university open days, since the GEAP period. | Given the commissions specific remit, we had great engagement with graduates, and therefore will speak with VPSC to rectify. | Annually in Decmeber | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Action 6.3 Where appropriate encourage women to apply for higher duties acting roles or promotions | Ongoing | Over 2022 and 2023 we have experience high growth at the commission, and have been actively encouraging gender diversity in our acting arrangements and promotions. In line with our recruitment practices, we have commitments made across internal movements to keep gender inclusion at the forefront. | We had 48 women across the commission either act in higher duties, be promoted, or move into secondments during the time of this 2023 progress report. Our CEO was also an Executive member who acted as the CEO, and then was successful in securing the role shortly after the reporting period. |  | People and Culture Senior Leaders/Managers | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Action 7.1 Encourage internal and external secondments where business needs allow it | Ongoing | In line with our high growth of roles at the commission, when People and Culture are providing support to hiring managers, they are reminded of, and encouraged to consider internal applicants or use inter agency and VPS connections in filling the role. The Jobs and Skills Exchange is frequently used by the commission in advertising and sourcing candidates. | In the 2023 audit, we have had 14 internal secondments, with this being a mix of senior leader and non senior roles. This does not include those roles we had on acting/higher duties arrangements. |  | People and Culture Senior Leaders/Managers | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Action 7.2 Create a new mentoring program with other departments and agencies | Complete | In 2023, we deployed our cross agency mentoring program. While we had not launched this by December 2022, we delayed it to be launched post summer break. The planning, logisitics and eligibility critera was completed by the December 2022 deadline. | Across the 5 agencies and departments, we had a total of 105 participants, either as a mentor or mentee. The essential services commission had a total of 29 participants, with 14 men and 15 women participating. | Due December 2022 | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Action 7.3 Continue to advertise L&D opportunities internal and external to the commission | Ongoing | As an ongoing action, we regularly advertise learning and development programs offerings via our intranet, dedicated microsoft teams channel for learning and development and our CEO weekly town hall. The staff across the commission regularly attend VPS innovation network webinars and forums, and we have dedicated training delivered with external vendors on First Nations Cultural Awareness, mental health and wellbeing training, safety and workplace behaviours. We will be further advertising and deploying L&D offerings in 2024 with the launch of our LMS. | All of our staff in 2023 were required to attend the First Nations, mental health and fair treatment in the workplace training, as part of commission commitments to workplace inclusion, health and safety. |  | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Action 7.4 Promote innovation network L&D opportunities | Ongoing | Ongoing as we regularly socialise the VPS innovation network through People and Cuture advisory, intranet and dedicated microsoft teams channel for learning and development. | N/A |  | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Action 7.5 Managers to assist in identifying learning and development needs and support staff to participate in appropriate learning and development. | Ongoing | As an ongoing action across the GEAP period, we have embedded this process as part of our PDP process. Managers are to discuss with their staff their goals for the upcoming financial year and as part of this process, assess their learning and development goals and identify any opportunities that support their career growth. | N/A |  | People and Culture Senior Leaders/Managers | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Action 8.1 Compulsory manager training on sexual harassment and fair treatment in the workplace. | Complete | Across June and July of 2022 all of the commission staff (incl managers) participated in 'fair treatment in the workplace' training. We maintained this participation by rolling out more across 2023 for the new starters, and then have committed to rolling this out in 2024. This training covers sexual harassment, victimisation and appropriate workplace behaviours as covered by our fair workplace policy. | N/A | Due July 2022 and June 2024 | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Action 8.2 Fair treatment training for all other staff available | Complete | Across June and July of 2022 all of the commission staff (incl managers) participated in 'fair treatment in the workplace' training. | N/A | Due December 2022 | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Action 8.3 Fair treatment in the workplace compliance module rolled out every two years | Complete | This action is complete/ongoing. Upon starting at the commission, staff are sent the fair treatment in the workplace training module as part of the onboarding process, and then reassigned the module every two years as a refresher. |  | Due June 2023 | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Action 8.4 Update fair workplace policy to ensure the method of reporting unfair treatment is clear and easy to follow | Complete | As part of the training released across the commission, we updated our fair workplace policy in December 2021, to update a new section 'responding to inappropriate workplace behaviour' with support on how to raise concerns, report and address different situations where this may be occuring. The policy also makes reference to the inappropriate workplace behaviour complaints procedure. |  | September - December 2021 | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 5
Action 8.5 Fair treatment in the workplace information is available on the intranet for all staff | Complete | After the fair treatment in the workplace policy was refreshed, we uploaded this under the policy section of our intranet, and communicated to staff where this information was hosted. |  | 2022-07-01 | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 6
Action 9.1 Ensure employee and manager toolkits are available and easy to find on the intranet | Complete | In December 2022, we uploaded information to our intranet relating to family violence and how staff can access support. In line with our commitments to family violence, we are currently in the process of further revising and updating this guide to be in line with best practice, due to be launched in March 2024. |  | Due December 2022 | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 6
Action 9.2 Conduct information sessions for staff and managers on community support | Complete | Across June 2022, we hosted various information sessions as part of progress updates one year after the launch of our external consumer strategy, 'Getting to Fair'. This session was run by members of our consumer vulnerability team with external community based organisations and our EAP provider along to present support information to our staff. |  | Due June 2022 | People and Culture Vulnerability project team | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 6
Action 9.3 Session for staff and managers on support available | Not started | While we completed the ongoing rollout of workplace behaviour and sexual harassment training in 2022 and 2023, and hosted the community support session on family violence,we are yet to roll out specific family violence training for internal processes. We are rolling out responding to disclosures training, a family violence Elearn and bystander intervention training across 2024. |  | N/A | People and Culture Vulnerability project team | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 6
Action 10.1 Ensuing up to date information on flexible work is readily available to staff on the intranet and at induction for new starters | Complete | As part of induction, onboarding, hiring and recruitment processes, templates and toolkits, we have outlined our commitment to flexibility. These reviews and updates were completed by June 2022. |  | June 2022, June 2024 | People and Culture Flexible work sponsor | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 6
Action 10.2 Create a new online flexible work form to make it easier for staff to request flexible work | Complete | In August 2022, we had ensured the system functionality to upload flexible work arrangements was integrated into our employee system, working with our HR shared services provider to implement this change. |  | Due August 2022 | People and Culture Flexible work sponsor | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 6
Action 10.3 Manager training on managing flexible work | Complete | Across 2022, we rolled out manager skill sessions on managing hybrid work and 'how-to' in creating flexible work cultures. We complemented this with further guidance and toolkits uploaded to our intranet, completed by the December 2023 timeframe. |  | Annually in Decmeber | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 6
Action 10.4 Ensure internal L&D offerings are offered online and face to face to accommodate for flexible work arrangements | Ongoing | All training offerings are offered in a hybrid format, or multiple mediums of the same topic will be deployed, such as a toolkits, eLearns and workshops to cater for different learning styles and arrangements. There is one expection to the hybrid offering when it comes to our flagship leadership program, but we make adjustments to this when formally requested. |  |  | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 6
Action 10.4 All roles at the commission are advertised as flexible. To do this we will need to work with HRSS to find a solution to ensure roles are advertised as flexible and come up in searches for full time and part time roles. | Complete | Since 2021, we have adjusted job advertisements and position description templates include a commitment to flexibility, diversity and caring responsibilites. This was an adjustment we made to the job advert template on JSE and Careers.vic This was completed in Decmeber 2022. We will continiously review in line with best practice. |  | Due December 2022 | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 6
Action 10.5 Create guidance for managers on supporting their staff while on parental leave and returning from parental leave to ensure working parents are not disadvantaged | Complete | In November 2022, we uploaded guidance on parental leave on our intranet, and updated our flexible work toolkit. We updated this again in October 2023, and will review as part of broader DEI reviews in 2024 and 2025. |  | 2022-11-01 | People and Culture | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 6
Action 10.6 Actively encourage parental leave and celebrate the secondary carers who take up the opportunity primary carer responsibilities | Not started | While uptake is increasing as seen as part of our indicators progress report, there is more to be done from an internal communications persepctive to celebrate and recognise those who take parental leave, especially those who take primary leave outside of the traditional gendered norms. This was due to commence in December 2022, and then as an ongoing action. We will rectify this through developing a strategic comms and events calender and process. |  |  | People and Culture Senior Leaders/Managers | bar: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 7
| Select one | #VALUE!
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. 1: Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | 2022 | People and Culture Corporate Support | bar: Relevant indicator(s) 1 to Relevant indicator(s) 3; Relevant indicator(s) 5 to Relevant indicator(s) 7
Note on C8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jessica Bryers (ESC) I have tagged you in a task on our submission planner, if ok to assist here - cross checking the status of each of these strategies (column b) against the GE progress tracker you shared. We can then both work through Column D together to answer the prompts. Reply: Thanks @Jakob Woods-Huxtable (ESC) I have filled in this one and column c in sheet 3. I have marked quite a few as ongoing because even though we have certain actions associated with each I am not sure work in these areas will ever be complete. We can chat about that when we go through column D.
Note on E10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Action 1.1 Success Indicator: - Diversity survey increases our understanding of intersectional attributes within the commission

## 2.2 Resourcing your GEAP
Resourcing your GEAP
Table 2.2 - Allocation of resources to implement the strategies and measures in your GEAP
Recommended
You might consider some or all of the following, in addition to any other aspects you consider relevant: • Who implements the strategies and measures in your GEAP? What role do they perform at what level in your defined entity? • How many staff members/FTE are allocated to implementing the strategies and measures? • Was enough resourcing allocated to successfully implement your strategies and measures? If not, how will this be addressed?
Your Comments
During the 2023 reporting period, the actions were allocated against the People and Culture remit leads - one being Leadership and L&D one being Insights, Data, Employee Relations and Performance Mgmt and the final one being OHS, Recruitment and People Operations. This was in the absence of the team having a dedicated diversity, equity, and inclusion (DEI) lead, and allowed the actions to be effectively embedded across the P&C remits in a small and lean team of 7. This meant leaders, managers, and executive were more involved in overseeing and sponsoring the actions across the commission. The People and Culture team also used the DEI working group as a source of feedback, consultation and support in gaining their insights from a lived experience persepctive. The People and Culture team also ensured that they engaged with relevant SMEs across the organisation, such as our consumer vulnerability team, strategic communciations team and our systems and technology teams to bring their expertise into the delivery of our DEI actions. This was allocated into the existing remits of 3 full time equivalent staff, while not specifically their sole remit on a full time basis. Each of the People and Culture remit leads utilised their own teams and direct reports, incoporating tasks as part of their roles and responsibilities. While there were three remit leads embedding DEI practices into their relevant areas, this resourcing was disrupted due to one of the remit leads going on parental leave, and the backfills remit being dedicated exclusively to refreshing our L&D and leadership process due to a high growth influx of leadership roles being created across the organsiation. While the role still balanced DEI responsibilities, some of the work was realigned. Since October 2023, a dedicated DEI lead position has been a part of the People and Culture team, to oversee the commissions holistic DEI efforts, and make systemic cultral changes to how we implement, measure and advance DEI.

## 3 Indicators
Workplace Gender Equality Indicators
Table 3 - Workplace gender equality indicators progress
Required | Required | Required | Recommended | [6 empty] | Recommended | Factors key:
|  |  | Factors | [7 empty] | a. b. c. d. e. f. g. | The size of the defined entity, including the defined entity's number of employees. The nature and circumstances of the defined entity, including any barriers to making progress. Requirements that apply to the defined entity under any other Act, including an Act of the Commonwealth. The defined entity's resources. The defined entity's operational priorities and competing operational obligations. The practicability and cost to the defined entity of making progress. Genuine attempts made by the defined entity to make progress.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
Gender composition of all levels of the workforce | Yes | More broadly, across the commission, in our 2023 audit our workforce composition consisted of 103 women (52%) and 93 men (47.55%). This was compared to our 2021 audit, where our workforce composition consisted of 78 women (50.6%) and 76 men (49.4%), showing a majority spilt for women, even as our headcount continues to grow. We still have the challenge of capturing staff who identify as gender diverse or non-binary across our systems, which is being worked towards as one of our 6 main operational projects, and is a commitment made in our GEAP. Our gender composition across role levels, with the exception of VPS 6 and senior leaders, are favouring women. Our VPS 6 role level in 2023 audit, shows 16 women (44.4%) vs 20 men (55.6%) compared to 15 women and 11 men respectively, showing headcount growth has favoured men in the VPS 6 space. In 2023, we redefined what a senior leader is across the organisation in line with the CGEPS definition of what classes as a senior leader, as we previously only counted exective as a senior leader. Our new definition of a senior leader is "someone VPS7 or above reporting directly into an executive member." Therefore in 2021, we only reported on executive members and in our 2021 audit, this was 5 executive members with one being a woman (20%) and four being men (80%). In our 2023 audit we had 22 senior leaders, with 10 being women (45.45%) and 12 being men (54.55%). Where we see the highest majority of women in the 2023 audit, would be our VPS 3, VPS 4 and VPS 5 role levels. Our VPS 5 role level in 2023 audit contains the most amount of roles, totalling 61. In our 2023 audit, 32 of these are women (52.4%) and 29 of these roles are men (47.5%), compared to our 2021 audit where the spilt was equal with 28 men and 28 women. Across our VPS 4 role level in our 2023 audit, 27 of these roles were women (54%) and 23 were men (46%) compared to 17 and 18 respectively in our 2021 audit. Across our VPS 3 role level in our 2023 audit, 14 of these roles were women (48.3%) and 10 were men (41.7%) compared to 14 and 6 respectively in our 2021 audit. While progress on average since our 2021 audit has favoured women, we have identified that the VPS 6 and senior leader cohorts have favoured men, which our GEAP has commitments made to advance development opportunties for women, and support women in male dominated roles.
Gender composition of governing bodies | Yes | Since submitting our 2021 audit, our governing body composition has not changed during the period of our 2023 audit. Our governing body consistents of 2 men and 2 women, which is 1 chair and 3 board members.
Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender | Yes | In our 2021 audit our mean total remuneration pay gap (GPG) was 8.1%, compared with 4% in 2023. In 2021, our highest GPG existed within the VPS 3-4 level, at 2.32%, with our lowest GPG being in the executive level at -2.71%. In 2023, our highest GPG existed within the SRM/STS level, at 2.20%, with out lowest GPG being in the executive level of -9.01%.
Sexual harassment in the workplace | No | In our 2021 audit, we had no reported incidents of sexual harrassment in the workplace and additionally there were no reported experiences in the 2021 People Matter Survey. In the 2023 People Matter Survey 4% of women reported experiencing sexual harassment. We did not receive any formal reports. We do not consider this progress against the indicator. Our focus is on refining our policies and procedures to ensure the process for reporting is clear and safe. Whilst we anecdotedly have a high degree of engagement from staff with our people and culture team we recognise that a lack of formal reporting could be indicative of a barrier. Our board and executive are passionate about leading this change as we increase our focus on safety and welbeing across all areas. Our 'Fair Treatment in the Workplace' training delivered to all staff in 2023 went into detail about these issues which certainly has increased understanding.
Recruitment and promotion practices in the workplace | Yes | In our 2023 audit, women represented 46 hires out of a total 83 recruitment appointments, which is a 55.4% majority (7.9% increase) compared to our 2021 audit, where women represented 47.5% of recruitment appointments (19 women out of 40 hires). This means in our 2023 audit, men represented 37/80 hires, compared to our 2021 audit where they represented 21/40. This increase is a positive growth, given we had a growth of recruitment appointments from the 2021 audit of 40 vs 83 in 2023 showing recruitment appointments have favoured women and shifted the majority. Out of those 46 hires that were women from our 2023 audit, 23 were full-time ongoing (vs 7 in 2021 audit), 19 were full time fixed term (vs 6 in 2021 audit), 1 was part time ongoing (vs 1 in 2021 audit), 1 was part time fixed term (vs 4 in 2021 audit) and 2 were casual (vs 1 in 2021 audit). No data is available for gender diverse and non-binary employees across both audits, as we use an external shared provider for payroll and employee data. As part of our GEAP, we have committed to improving our data collection and employee demographics s processes, under actions 1.1 ' Encourage commission staff to share relevant intersectional data'. In our 2023 audit, we had a total of 18 promotions, with 9 being women (50%) and 9 being men (50%). In our 2021 audit, we had 22 total promotions, with 15 of these being women (68.1%), and 7 men (31.82%). This was across all levels (VPS 4 - SES 2). I. This is reflective of perm promotions not being so prevelant due to the shifting nature and growth of the commissions remit, seeing more higher duties and acting arrangements put into place through business and divisonial team movements as holding patterns. In 2023 audit, there were a total of 59 higher duties and acting arrangements, with 32 being women (54.2%) and 27 (45.76%) being men compared to our 2021 audit where there a total of 50 higher duties and acting arrangements, with 26 being women (52%) and 24 being men (48%).
Availability and utilisation of terms, conditions and practices relating to: - family violence leave; and - flexible working arrangements; and - working arrangements supporting employees with family or caring responsibilities | Yes | In our 2023 audit, we had 9 women take parental leave, with 149.4 weeks of paid leave, and 201.05 weeks of unpaid leave. We also had 6 men take 48.47 weeks of paid leave.In our 2021 audit, we had 8 women take parental leave, with 138.7 weeks of paid leave and 59 weeks of unpaid leave. We had 7 men take 21.2 weeks of paid leave. While our amount of women in 2023 taking leave increased, as did their weeks of leave, and we had 1 less man take parental leave, the amount of paid leave for men increased, with our data showing some men took the additional primary carer leave offering to support their partner and take on additional responsibilties once the original primary carer has returned to work. This is progress as we have more people taking leave, paid and unpaid, and a shift in the amount of primary leave from men. Over 2022 - 2023, we updated our communications and resources to further encourge men to take parental leave, showing this had impact. In 2023 audit, we had no official disclosures of family violence, therefore no leave was taken. In our 2021 audit, this is the same. Although we have heard more informal conversations and request for information on the topic as we increase our support mechanisms and training in this space. While we had no official disclosures, it is comforting to see our 2023 Peoples Matters result for "My organisation would support me if I needed to take family violence leave" question saw a 92% positive response rate, +5% from 2021. Note our People Matters participation rate was 70%.
Gendered segregation within the workplace | Yes | In 2023 audit, 3 out of 5 of our divisions had more women than men, with the highest division being the office of the CEO with 16 women vs 2 men, which is predominately executive assistants, communications managers, admin support staff. 1 division has equal gender spilt of 26 men and 26 women. 1 division therefore has more men than women, which is our Energy Upgrades division, with 33 women vs 37 men, only at a -4 variance. This division is predominately auiditing staff, tech/software engineers, enforcement and compliance. Our 2021 audit data did not include the divisional breakdown for a direct comparison, but our employee data from that period shows that two divisions had more men than women. Consistent with our increase in appointment of women via our recruitment process, we consider this progress against the indicator.
Example(s)
Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  | a | b | c | d | e | f | g
Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.
Note on B12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nick Godfrey (ESC) is this possible without a GPG done?
Note on D8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nick Godfrey (ESC) next Tuesday, is where you will come In handy. Next Monday Jess and I will attempt to write these using the data you put together, but will need you to validate and review our analysis for each indicator using fresh eyes.

## Examples (hidden)
1 Gender impact assessments
| Title | Subject | Description | Status |  |  | Confirm if actions taken |  |  |  | Describe actions taken |  | Confirm intersectionality considered |  | Explain intersectional lens applied
| What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. |  |  | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. |  |  |  | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. |  | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. |  | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
| Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review |  |  | Yes |  |  |  | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. |  | Yes |  | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.
2.1 Strategies and measures
| Strategies and measures | Status | Status description | Evaluation of success | [6 empty] | Timeline | Responsible | Relevant indicator(s)
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | [6 empty] | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Relevant indicator(s) 1: Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator.
| Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | [6 empty] | 2022 | People and Culture Corporate Support | bar: Relevant indicator(s) 1 to Relevant indicator(s) 3; Relevant indicator(s) 5 to Relevant indicator(s) 7
3 Workplace Gender Equality Indicators
| Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  |  | a | b | c | d | e | f | g
| This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
| Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
| Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## (Hidden) REF (hidden)
Policy | New | Yes | Select one | Yes
Program | For Review | No | Complete | No action taken
Service |  |  | In progress
Ongoing
Not started
Void/cancelled